## Product Backlog
Issue # | ID | User story | Associated Tasks | Story points associated to a US | Priority (High, Medium, Low) | Risk
2 | US.01 | As a student when accessing the website, the user wants to be welcomed with a login/registration page | - Create a login/registration page UI shown when the site is accessed - Add an email input field - Add a password input field - Add a Sign Up option on the page - Add a Login option on the page - Implement password verification on the password field | 4 | High | HIGH - User can't use app if there is no option to sign up or login
7 | US.02 | As a user, I want my login information to be authenticated so that I can access the home page securely. | - Create a function to authenticate user credentials against those stored in the database - Allow access to the home page upon authentication - Create a function that welcomes the user into the home page - Add a Logout button - Redirect the user to the login page on logout | 8 | High | HIGH - authentication is the gateway into the app, have to ensure data privacy is maintained
12 | US.03 | As a user, I want to access a dashboard so that I can navigate MealMajor easily | - Design basic dashboard layout - Add navigation links (Profile, Recipes, Planner) | 5 | High | HIGH - user cannot have access to the website's functionalities without navigation links
15 | US.04 | As a user I want to create a profile that suits me and be able to manage it (allergies, diets) | -Design a short quiz/ survey to collect user's information such as diet preferences, allergies, etc. -Profile saves in database | 6 | High | HIGH - meal planner has a high reliance to this feature, and user must be informed of the safety implications of each recipe
18 | US.05 | As a user, I want the ability to create recipes that will be available on demand, to edit their information once created, and to delete them if needed. | - Create a modal that will accept and save the recipe's information as its inputs once the "New Recipe" button is clicked - Create an edit modal to edit the recipe's information once the "Edit" button is clicked - Remove a recipe from the database as well as from the website once the "Delete" button is clicked | 9 | High | HIGH - main functionality of the website relies on this feature being created
22 | US.06 | As a user, I want to be able to specify the ingredients, preparation time, prepration steps and cost of the recipes I create. | - Add an input field to the modal for the ingredients - Add an input field to the modal for the preparation time - Add an input field to the modal for the preparation steps - Add an input field to the modal for the cost | 3 | Medium | MEDIUM - the recipe objects will be available, but their respective details remain an important part
24 | US.07 | As a user, I want the ability to view all the recipes I have made so far, and to see their respective information when I click on one of them. | - Design a UI page to view all current recipes - Create a recipe UI element that will display its name, preparation time, and picture - Create a "New Recipe" button - Create an "Edit" button for every recipe - Create a "Delete" button for every recipe | 7 | Medium | MEDIUM - the recipe data will all be present, but this feature will ensure that it is accessible and well-presented to the users
28 | US.08 | As a user, I want to be able to search and filter the recipes that I have created | - Add a search box that searches through all available recipes - Add the option to filter the search by time, difficulty, cost, dietary tag, etc. | 4 | Low | LOW - searching and filtering don't affect the main functionality of the website
N/A | US.09 | As a user, I want to create a weekly meal plan | -Add a function to create a weekly meal plan according to the user's profile and preferences - View meals in a grid format (create another UI) -Avoid duplicate meals in the same week | 10 | High | HIGH - it is a major use case of the website's functionality
N/A | US.10 | As a user, I want the ability to edit or remove meals from the weekly planner | - Add a function to edit a meal - Add a function to delete a meal | 5 | Medium | MEDIUM - not a main functionality as the weekly planner still works fine
N/A | US.11 | As a user, I want the ability to assign recipes to a day of the week and to meal type | -Add a function to assign a recipe to a certain day of the week -Add a function to assign a recipe to a certain meal type (breakfast/lunch/dinner/snack) | 5 | Low | LOW - this is an extra functionality that will enhance the user experience but that is by no mean essential
N/A | US.12 | As a user, I want the ability to calculate the total calories and macronutrients of all recipes assigned to a specific day so that I can easily track my daily nutritional intake | - Add “Calculate Calories” button and results UI display - Send data to AI API for nutrition analysis Process and display total calories and macros | 10 | Low | LOW - this is an extra functionality that will enhance the user experience but that is by no mean essential

## Overview
NomNom Labs
Prepared By:
Gerom Fazaa
Ryan Jugmohun
Kevin Rizkallah
Matthew Vanstone-Cadogan
Minh Giang Chiem
Mark Samuel

## Sprint1
Issue # | Story ID | Task | Responsible | Due date
3 | US.01 | Setup login/registration page UI that includes an input field for the email and password | Minh Giang / Gerom | 2026-02-02
4 | US.01 | Implement password validation rules that check length, upper/lowercase and no underscores | Kevin / Gerom | 2026-02-02
5 | US.01 | Add a login button that triggers user authentication function and displays errors for invalid credentials | Minh Giang / Gerom | 2026-02-02
6 | US.01 | Add a register button that triggers user creation after validation passes and shows feedback for existing account & suboptimal password | Minh Giang / Gerom / Mark / Kevin | 2026-02-02
8 | US.02 | Create function to authenticate a user by comparing credentials with stored values in database and returns error messages on failure. | Matthew / Gerom | 2026-02-06
9 | US.02 | Implement route protection to prevent access to home page unless user is authenticated and to redirect unauthenticated users back to the login page. | Mark / Gerom | 2026-02-06

## Sprint2
Issue # | Story ID | Task
13 | US.03 | Design the dashboard layout that you are redirected to upon login as well as the navigation UI
14 | US.03 | Add navigation links to "Profile" and "Meal Planner"
16 | US.04 | Design a modal in profile management to collect diet preferences as well as allergies
17 | US.04 | Save diet preferences and allergies to the database
19 | US.05 | Design a modal that appears when "New Recipe" is clicked to input new recipe information and save the information to the database
20 | US.05 | Design a modal that appears when "Edit Recipe" is clicked to modify a recipe's information and save the information to the database
21 | US.05 | Code the deleting logic to remove a recipe from the recipe manager & database when "Delete Recipe" is clicked
31 | US.05 | Design the layout and styling of recipe modals and action buttons.
23 | US.06 | Add an input to the recipe modals for ingredients, preparation time, preparation step, difficulty and cost
25 | US.07 | Design a UI element for every recipe in the recipe manager that includes the name, preparation cost, and picture
26 | US.07 | Create "Edit Recipe" & "Delete Recipe" buttons for each recipe
27 | US.07 | Implement a recipe information display
29 | US.08 | Add a search box that searches through all the current recipes
30 | US.08 | Add the option to filter by: time/difficulty/diet/cost

## Sprint3
issue # | Story Id | Task
36 | US.09 | Create weekly planner UI (grid)
37 | US.09 | Generate meal plan based on user preferences
38 | US.09 | Prevent duplicate meals in the same week
39 | US.09 | Handling no recipes, missing preferences, generation issues
41 | US.10 | Add edit/delete buttons in planner
42 | US.10 | Implement edit and delete logic
43 | US.10 | Update planner after changes
44 | US.10 | Handling delete fail, edit not saved, invalid input
46 | US.11 | Assign recipe to a day
47 | US.11 | Select meal type (breakfast/lunch/dinner/snack)
48 | US.11 | Save assignments to planner
49 | US.11 | Handling invalid assignment, missing data, conflicts
51 | US.12 | Add a “Calculate Calories” button
52 | US.12 | Add a "Macros" row to the meal planner table
53 | US.12 | Display macronutrient quantities (protein, carbohydrates, fat) and total calories for every cell in the "Macros" row
54 | US.12 | Collect recipe data from meal planner, send to AI API for analysis, and display computed macros + calories when "Calculate Calories" is clicked

## Sprint4
issue | Story Id | Task
55 | US.13 | Finalize and polish the unique feature
56 | US.13 | Finalize and improve overall CSS styling
57 | US.13 | Finalize and improve overall CSS styling
58 | US.13 | Finalize and improve error handling across the application
59 | US.14 | Perform unit testing for core functionalities
60 | US.14 | Set up and validate CI/CD pipeline
61 | US.14 | Perform acceptance testing to validate requirements