## Sheet1
Sprint 1 Plan
Issue # | User story | Associated Tasks | Story points associated to a US | Priority (High, Medium, Low) | Risk | Responsible | Due date
1 | As a student accessing the website, I want to be welcomed with a login/registration page. | Design login and registration UI Create email and password input fields Add form validation (required fields) | 3 | High | HIGH – users cannot access the app without this page
2 | As a user, I want my password to be validated so that my account remains secure. | Enforce password length rules Validate upper/lowercase requirements Display validation feedback to user | 2 | High | HIGH – weak validation compromises security
3 | As a user, I want my credentials to be authenticated so that I can access my account securely. | Create authentication function Validate credentials against database Handle invalid login attempts Redirect authenticated user to dashboard | 4 | High | HIGH – authentication is crucial to the system
4 | As a logged-in user, I want to log out so that my account remains secure. | Add logout button to navigation bar Clear user session on logout Redirect user to login page | 2 | High | MEDIUM – improper logout may leave session active
5 | As a logged-in user, I want to access a dashboard so that I can navigate the application easily. | Design basic dashboard layout Add navigation links (Profile, Recipes, Planner) Restrict access to authenticated users only | 4 | High | HIGH – navigation is required to access features